## Fundraising
Local Community Foundation - Endowment Campaign
| Donor Groups | SMART Goals | Fundraising Activity | Communication Plan | Team Members | Est. Revenue | Est. Expense | Due Dates
January | Donor retention | Have 15% of current donors donate to the endowment campaign | Donor Appeal #1 - Announcing Endowment Campaign | Email and/or mail appeal, email and/or mail thank you |  | 1500 |  | 2024-01-24
| New Donors | Add 5 new donors | Announce Endowment Campaign in Newspaper/Radio | Send press release to newspapers and radio stations |  | 500 |  | 2024-01-31
Donor upgrades
February | Donor retention
| New donors | Add 5 new donors | Announce Endowment Campaign on radio station | Board member (or two) are interviewed on radio station |  | 500 |  | 2024-02-15
| Donor upgrades | Increase recurring monthly contributions to $1,000 | Donor Appeal #2 - Asking for Recurring Monthly Contributions | Send email and/or mail appeals to annual donors and friends of community foundation, email and/or mail thank you |  | 1000 |  | 2024-02-25
March | Donor retention |  | Donor Update #1 - Update current donors on progress in endowment campaign | Send email
| New donors | [6 empty] | 2024-03-15
| Donor Upgrades | Add 1-2 new planned gifts | 1-to-1 coffee with 5 potential major donors interested in the Montana Endowment Tax Credit | Personal phone calls to each donor, follow-up thank you calls |  | 2500 |  | 2024-03-31
April | Donor retention |  | "Grantee Showcase" at Backporch BBQ | Email invite |  |  |  | 2024-04-12
| New donors | Receive donations from 2-3 businesses in town | 1-to-1 coffee with 5 potential major business donors | Personal phone calls to each business, follow-up thank you calls |  | 1000 |  | 2024-04-30
Donor Upgrades
May | Donor retention |  | Donor Update #2 - Update current donors on progress in endowment campaign | Send email
| New donors | Add 10 new donors | House Party | Email invite and phone call follow-ups |  | 1500 | 500 | 2024-05-11
Donor upgrades
June | Donor retention
New donors
Donor Upgrades
July | Donor retention | Celebrate those who have given to the endowment campaign | Community BBQ | Email invite with personal phone call follow-ups |  |  | 500 | 2024-07-05
| New donors | Add 5 new donors | Community Parade/Concert | Board member (or two) talks about the endowment campaign at community events |  | 500 |  | 2024-07-05
Donor upgrades
August | Donor retention
New donors
Donor upgrades
September | Donor retention |  | Donor Update #3 - Update current donors on progress in endowment campaign | Send email
New donors
Donor Upgrades
October | Donor retention
New donors
Donor Upgrades
November | Donor retention
| New donors |  | Launch peer-to-peer fundraising campaign | Email, social media, Giving Tuesday livestream | Board and volunteers | 500 |  | 2022-11-29
| Donor Upgrades |  | Auto-renewal for monthly donors | Personalized thank you messages |  | 500
December | Donor retention | Receive end-of-year gifts from 30 current donors | Holiday card and annual newsletter | Mail cards and newsletters |  | 1500 | 200
| New donors | Add 20-30 new donors | Annual newsletter to everyone in the county | Mail newsletters |  | 1500 | 300
| Donor Upgrades |  | Donor Appeal #4 - End-of-Year Giving | Personalized appeals / phone call follow-up |  | 500 |  | 2022-12-31
TOTAL | [5 empty] | 13500 | 1500 | 12000